## Sheet1
Description | Likelihood | Impact | Mitigation Plan | Contributor Name | Date | Description
Familiarity with chosen framework and languages | 1 | 2 | This has been downgraded to a one because our group has a good handle on the languages chosen.
Web scraping | 0 | 5 | We have pulled all the data and cleaned some of the tags.
Front End/Back End integration | 0 | 2 | We have our routing setup and the front and back end are collaborating fine using the API
Attributes don’t map nicely for products | 2 | 4 | We have cleaned most of the tags, however some products have tags that are missleading.
Setting up channels using top tags | 2 | 5 | We have began the process of picking the top tags that are viable for channels. This could still be a problem moving forward, however it appears that we have a decent handle on it.
Setting up the database to be able to be accessed anywhere | 1 | 2 | This seemed to have been solved, however there seems to be some compatiblity problems with certain types of inserts. We plan to see how to change our queries in Sprint 4.
Suggestion Algorithm Implementation | 4 | 5 | Currently having some doubts about using Naive Bayes formula. Having initial problem with calculating what a user will do next.
Domain Name Set up | 0 | 3 | Domain name is in place now. The problem resides in the database that is on our server.
Loading data from the scraper into the database | 0 | 4 | We have fixed the issue with loading data into database on the server
Data privacy | 1 | 1 | Still need to add the hide function for profiles. Also we are considering making users have preferences to have a private account.
Creation of a mobile app | 5 | 3 | We are currently doing research on the mobile and learning the languages needed to make these applications. Currently Kyle is having a lot of issues with the mobile app
Integrating machine learning into backend | 3 | 5 | We are doing independent implementation of the machine learning algorithms. This may lead us to having a problem with integrating it later on
Integrating mobile app with the website back end | 2 | 5 | We are looking at hooking the mobile app up to our API to integrate it to the back end of the website. This could cause issues later on.